Event: Breakfast for Laborers

Date:  25 February 2026

Time

| Date | Time | Hours | Activity |
| --- | --- | --- | --- |
| 15 February | 8pm - 11pm | 5 Hour | First briefing session about the project |
| 16 February | 3pm - 8pm | 8 Hours | Developing the concept and planning |
| 17 February | 6pm - 10pm | 5 Hour | Identifying locations and target group |
| 18 February | 2pm - 10pm | 10 Hours | Meeting with suppliers and sourcing materials |
| 19 February | 1pm - 6pm | 5 Hours | Preparing a detailed budget and logistics plan |
| 20 February | 1pm - 4pm | 3 Hours | Reviewing project steps with volunteers |
| 21 February | 1pm - 9pm | 7 Hours | Designing promotional materials and final preparations |
| 22 February | 5pm – 10pm | 5 Hours | Recruiting and training volunteer team |
| 23 February | 1pm - 8pm | 7 Hours | Purchasing food and packaging supplies |
| 24 February | 1pm - 9pm | 10 Hours | Packaging and organizing breakfast kits |
| 25 February | 7am -9am | 2 Hours | Event: Distributing breakfast to laborers |
| 26 February | 2pm - 10pm | 8 Hours | Documentation, feedback collection, and project review |
| 27 February | 4pm – 9pm | 5 Hours | Preparing Post Event Report |

Total Hours: 80 Hours