| Time | Activities | Notes |
| --- | --- | --- |
| Saturday, 6th March 2021 *1 hour |  |  |
| 03:00PM – 04:00PM | Meeting (Forming). | Assigning position for each committee. |
| Sunday, 7th March 2021 *2 hours |  |  |
| 11:00AM – 01:00PM | Meeting (Planning). | Choosing 2 games to play during the event and assigning roles to committee members. |
| Saturday, 13th March 2021 *3 hours |  |  |
| 8:30PM – 11:30PM | Meeting (Planning). | Choosing which game to play, as well as playing the games to see if they are interesting. |
| Sunday, 14th March 2021 *2 hours |  |  |
| 10:30AM – 12:30PM | Meeting (Planning). | Make preparations on how and where the event will be held. |
| Saturday, 20th March 2021 *5 hours |  |  |
| 10:00AM – 01:00PM | Poster design. | Design poster for the event. |
| 08:30PM – 10:30PM | Poster editing | Editing the poster. |
| Sunday, 21st March 2021 *2 hours |  |  |
| 02:30PM – 04:30PM | Budget planning. | Planning budget for the event. |
| Saturday, 27th March 2021 *2 hours |  |  |
| 08:30PM – 10:30PM | Meeting. | Discussion about the event date, time, & editing the postertitle. Do some corrections for the proposal reports. |
| Monday, 5th April 2021 *2 hour |  |  |
| 09:00PM – 11:00PM | Meeting. | Finalize and combine the proposal report. |

Minutes of Meeting – (SAMPLE)